## Planner
Requirement Unclear | Requirement Unclear | Task Name | Accountable | Status1 | Demo/Training | Start Date | Beta Realease | PROD Release | 24 Apr | 28 Apr | 01 May | 05 May | 08 May | 12 May | 15 May | 19 May | 22 May | 26 May | 29 May | 02 Jun | 05 Jun | 09 Jun | 12 Jun | 16 Jun | 19 Jun | 23 Jun | 26 Jun | 30 Jun | 03 Jul | 07 Jul | 10 Jul | 14 Jul | 17 Jul | 21 Jul | 24 Jul | 28 Jul | 31 Jul | 04 Aug | 07 Aug | 11 Aug | 14 Aug | 18 Aug | 21 Aug | 25 Aug | 28 Aug | 01 Sep | 04 Sep | 08 Sep | 11 Sep | 15 Sep | 18 Sep | 22 Sep | 25 Sep | 29 Sep | 02 Oct | 06 Oct | 09 Oct | 13 Oct | 16 Oct | 20 Oct | 23 Oct | 27 Oct | 30 Oct | 03 Nov | 06 Nov | 10 Nov | 13 Nov | 17 Nov | 20 Nov | 24 Nov | 27 Nov
FALSE | No | Claims |  |  | NA
FALSE | No | Claims Inflow |  |  | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Submission thru Portal |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Claims Management |  |  | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Claims Workflow |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Edit Claims / Claims Adjudication |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Claims Related Notifications (to Repair Facility) |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Claims Payments |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Claims Inspection Check Integration |  | Phase 2 | NA
FALSE | No | Data Migration: Claims |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Lemon Squad API Integration |  | In Review | NA | Thu Jun 19, 2025 | Mon Jul 07, 2025 | Mon Jul 14, 2025
FALSE | No | Carfax API Integration |  | Phase 2 | NA
FALSE | No | Claims AP |  |  | NA
FALSE | No | (Process assumes status = APPROVED to PAY) |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Payment Issued (VC, M1, AMEX, ACH, or Check) |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Claim Marked as Paid (ACH or Check) |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Claim Marked as Paid (when VC, M1, AMEX clears) |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
TRUE | Yes | Reconcile payment to claim. Account for overages/shortages |  | Not Started | NA
TRUE | Yes | Claims Credits |  | Not Started | NA
TRUE | Yes | Journal Entries to QB |  | Not Started | NA
FALSE | No | Claim Paid to Cash Recon |  | In Review | NA | Mon Aug 18, 2028 | Thu Aug 28, 2025 | Mon Sep 1,2025
FALSE | No | Dashboard |  |  | NA
FALSE | No | Servicer Role - Actionable Dashboard |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Claims Manager |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Agent (partial) |  | In Progress | NA | Wed Aug 27, 2025 | 2025-09-18
FALSE | No | Adjuster |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Heads Up |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Claims AP |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
FALSE | No | Claims Part |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Mon Jul 28, 2025
TRUE | Yes | Reports |  |  | NA
TRUE | Yes | Exceptions Pd by Claim Exception Fund |  | Not Started | NA
TRUE | Yes | Exceptions Pd by Commission Deduct |  | Not Started | NA
TRUE | Yes | Exceptions Pd by Deduct from Reinsurance |  | Not Started | NA
TRUE | Yes | Ensure that Lemon Squad/Snapsheet/Roadside are entered to claim |  | Not Started | NA
FALSE | No | Claims Payments |  | Not Started | NA | Mon Aug 18, 2028 | Thu Aug 28, 2025 | Mon Sep 1,2025
TRUE | Yes | Reporting |  | Not Started | NA
TRUE | Yes | Apply Payment from Claim Exception FIFO basis |  | Not Started | NA
TRUE | Yes | Email w/ attachment |  | Not Started | NA
FALSE | No | Dealer Management |  |  | NA
FALSE | No | Onboarding through Portal - v1 (As in PCRS) |  | In Review | NA | Thu Jun 26, 2025 | Mon Jul 14, 2025 | Mon Jul 21, 2025
FALSE | No | Onboarding through Portal - v2 (Configurable and changes in the Commission tab) |  | In Review | NA | Mon Aug 18, 2025 | Thu Sep 04, 2025
FALSE | No | Zoho Integration | Gayatri Raol | In Progress | NA | Mon Aug 18, 2026
FALSE | No | Onboarding through Email |  | In Review | NA | Mon Aug 18, 2027 | Thu Sep 04, 2025
FALSE | No | Setup and Manage |  | In Review | NA | Mon Aug 18, 2028 | Thu Sep 04, 2025
FALSE | No | Collection W9 Information |  | In Review | NA | Thu Jun 26, 2025 | Mon Jul 14, 2025 | Mon Jul 21, 2025
FALSE | No | Collection/Entry/change of ACH Information |  | In Review | NA | Thu Jun 26, 2025 | Mon Jul 14, 2025 | Mon Jul 21, 2025
FALSE | No | Dealer Rate Sheets |  | In Progress | NA | Mon Aug 18, 2028
FALSE | No | Dealer Groups |  | In Review | NA | Thu Jun 26, 2025 | Mon Jul 14, 2025 | Mon Jul 21, 2025
FALSE | No | Support Menu: F&I | Naresh Pansuriya/Shivani | In Progress | NA
FALSE | No | Support Menu: PEN | Naresh Pansuriya/Shivani | In Progress | NA
FALSE | No | Support Menu: iTap |  | Phase 2 | NA
FALSE | No | Support DMS: DealerTrack | Naresh Pansuriya/Shivani | Waiting | NA
TRUE | No | Support DMS: MenuMetric/Vision Dealer (new added on sep 16th) | Naresh Pansuriya/Shivani | Change | NA
FALSE | No | Test Rate |  | In Review | NA | Mon Aug 18, 2028 | Thu Sep 04, 2025
FALSE | Yes | Support ACH using PLAID |  | Discontinued | NA
TRUE |  | Support ACH and CC STRIPE | Nareshbhai | Not Started
FALSE | No | Data Migration: Dealer Rate Sheets | Nareshbhai | In Progress | NA | Mon Aug 18, 2028 | Thu Sep 04, 2025
FALSE | No | Autohouse |  |  | NA
FALSE | No | AutoHouse: Setup |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Autohouse: Writes Contracts |  | Hold | NA
FALSE | No | Autohouse: Remits Contracts |  | Hold | NA
FALSE | No | Autohouse: Cancels Contracts |  | Hold | NA
FALSE | No | All other Dealerships |  |  | NA
FALSE | No | Other Dealerships - Onboarding/Setup/Verify |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Agents Management |  |  | NA
FALSE | No | Setup New Agent |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Agent Rate Sheet |  | In Progress | NA
FALSE | No | Manage Agent |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Autohouse: Agent Setup |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
TRUE | Yes | Other Agents - Setup/Verify |  | Not Started | NA
FALSE | No | Contracts |  |  | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | New Contract Wizard |  | In Review | NA | Thu Jun 19, 2025 | Mon Jul 07, 2025 | Thu Aug 14, 2025
FALSE | No | Front End |  | In Review | NA | Thu Jun 19, 2025 | Mon Jul 07, 2025 | Thu Aug 14, 2025
FALSE | No | Import |  | Rework | NA
FALSE |  | Extract and import Email PDF contracts |  | In Progress
FALSE | No | API |  | Rework | NA
FALSE | No | Save as Draft |  | In Review | NA | Thu Jun 19, 2025 | Mon Jul 07, 2025 | Thu Aug 14, 2025
FALSE | No | Contract Management |  |  | NA
FALSE | No | Edit Contract |  | Rework | NA
FALSE | No | Transactions, Claims List |  | In Review | NA | Mon Aug 18, 2028 | Thu Aug 28, 2025 | Mon Sep 1,2025
FALSE | No | Save as Draft and AutoDelete |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Data Migration: Active Contracts |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Data Migration: Canceled/Inactive Contracts |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Contract Admin |  |  | NA
FALSE | No | Receive Remittances - Automated |  | Rework | NA
FALSE | No | Receive Remittances - Manual |  | Rework | NA
TRUE | Yes | Application of Cash |  | Not Started | NA
TRUE | Yes | Refund Overages/Bill Shortages |  | Not Started | NA
TRUE | Yes | Bounced Payments |  | Not Started | NA
FALSE | No | Sales/Remittance Registers |  | Rework | NA
TRUE | Yes | Adjustments/Reinstatements on contracts |  | Not Started | NA
TRUE | Yes | Contract Business to Cash Reconciiation |  | Not Started | NA
FALSE | No | Ability to mass void /reject contracts |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
TRUE | Yes | Reporting on voided/rejected contracts |  | Not Started | NA
TRUE | Yes | Rerate contracts for amounts/ payees/ changes/ updates |  | Not Started | NA
TRUE | Yes | Journal Entries to QB |  | Not Started | NA
FALSE | Yes | Contract Cancellation |  |  | NA
FALSE | No | Cancellation Processing |  | In Progress | NA | Fri Aug 29, 2025 | Thu Sep 18, 2025
FALSE | No | Dealership ability to initiate Quotes or Cancellation & Notifiy Ascent |  | In Progress | NA | Fri Aug 29, 2025 | Thu Sep 18, 2025
FALSE | Yes | Initiate Process upon receipt of request |  | In Progress | NA
TRUE | Yes | Review for Dealer Status, NCB, Claims Paid, Cancel Fees |  | Elicit Requirment | NA
FALSE | No | Lender Direct Cancellations (L5, Budco) |  | In Progress | NA | Fri Aug 29, 2025 | Thu Sep 18, 2025
TRUE | Yes | Diversicare Cancellations |  | Not Started | NA
TRUE | Yes | Cancel Business to Cash Recon |  | Not Started | NA
FALSE | Yes | Refund Type? Dealer Stmt Credit? Check or ACH |  | In Progress | NA | Fri Aug 29, 2025 | Thu Sep 18, 2025
TRUE | Yes | Prepare NACHA file for ACH Payments | Shivani Chinial | Not Started | NA
TRUE | Yes | Prepare check file to import into QB | Shivani Chinial | Not Started | NA
TRUE | Yes | Commissions |  |  | NA
TRUE | Yes | Reconcile 908 to 600 Activation Basis | Upendra Chaudhari | Not Started | NA
TRUE | Yes | Prepare Statements | Upendra Chaudhari, Nareshbhai | Not Started | NA
TRUE | Yes | Prepare Commission Summary Reporting RTP681 Sales Commission Report | Upendra Chaudhari, Nareshbhai | Not Started | NA
TRUE | Yes | PM Carry Forward to Summary | Upendra Chaudhari, Nareshbhai | Not Started | NA
TRUE | Yes | Incorporate additions for advances/loans | Upendra Chaudhari, Nareshbhai | Not Started | NA
TRUE | Yes | Incorporate deductions for claims exceptions | Upendra Chaudhari, Nareshbhai | Not Started | NA
TRUE | Yes | Incorporate deductions for contract/surcharge payments | Upendra Chaudhari, Nareshbhai | Not Started | NA
TRUE | Yes | Incorporate deductions for advance/loan payback | Upendra Chaudhari, Nareshbhai | Not Started | NA
TRUE | Yes | Incorporate Payee Corrections/Calculations | Upendra Chaudhari, Nareshbhai | Not Started | NA
TRUE | Yes | Prepare NACHA file for ACH Payments | Upendra Chaudhari, Nareshbhai | Not Started | NA
TRUE | Yes | Prepare check file to import into QB | Upendra Chaudhari, Nareshbhai | Not Started | NA
FALSE | No | Commissions Notification |  |  | NA
TRUE | Yes | Email Statements to Payees |  |  | NA
FALSE | No | Reinsurance |  |  | NA
FALSE | No | Configuration: Capture Deal |  | Not Started | NA | Fri Sep 05, 2025 | Thu Sep 25, 2025
FALSE | No | Claims Reserves |  | Not Started | NA | Fri Sep 05, 2025 | Thu Sep 25, 2025
FALSE | No | Earnings |  | Release | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Enter Expenses Paid/collected on Behalf |  | Rework | NA | Fri Sep 05, 2025 | Thu Sep 25, 2025
FALSE | No | Rule Engine to setup Coverages, Rate Bucket, Seller and Allocation |  | Not Started | NA | Fri Sep 05, 2025 | Thu Sep 25, 2025
FALSE | No | Bank configuration and entering bank transactions |  | Not Started | NA | Fri Sep 05, 2025 | Thu Sep 25, 2025
FALSE | No | Listing of Transactions and ability to add Adjustments |  | Not Started | NA | Fri Sep 05, 2025 | Thu Sep 25, 2025
FALSE | No | Dashboard for respective Reinsurance |  | Phase 2 | NA
TRUE | Yes | List of All Payments Due (Cession Funding) |  | Not Started | NA
TRUE | Yes | List of all amounts to be collected (Reverse Cession Funding) |  | Not Started | NA
TRUE | Yes | Journal Entries to Book |  | Not Started | NA
TRUE | Yes | Cession Statements (Net) RPT901 - Cession Statement |  | Not Started | NA
TRUE | Yes | Cession Statements (Retail) |  | Not Started | NA
TRUE | Yes | Reconcile Biz to Reins Accounts |  | Not Started | NA
TRUE | Yes | Reconcile Biz to Dealer Remittance |  | Not Started | NA
TRUE | Yes | Reconcile Claims to Reins Accounts |  | Not Started | NA
TRUE | Yes | Monthly Cash Analysis |  | Not Started | NA
TRUE | Yes | Summary by Product |  | Not Started | NA
TRUE | Yes | Contract Details |  | Not Started | NA
TRUE | Yes | Claims Details |  | Not Started | NA
TRUE | Yes | Reporting Packages (bolted together) |  | Not Started | NA
TRUE | Yes | Trust /Custody/B Account Stmts (Bolt into Package) |  | Not Started | NA
TRUE | Yes | Reporting Quarterly Cover |  | Not Started | NA
TRUE | Yes | Report of Reinsurer Collateral |  | Not Started | NA
TRUE | Yes | Report of Reinsurers by Domicile |  | Not Started | NA
FALSE | No | Coverage management |  |  | NA
FALSE | No | Coverage and details |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Product Development |  |  | NA
TRUE | Yes | Product (Coverage) Build - Workflow? |  | Not Started | NA
FALSE | No | Coverage Ratesheets (incl. Export and Import) |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Clone Coverage |  | Phase 2 | NA
FALSE | No | Test Rate (verify at product level) |  | Phase 2 | NA
FALSE | No | Data Migration: Brands, Product Types |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Data Migration: Coverage Groups and Coverages |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Data Migration: Loss Codes |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Data Migration: Surcharges |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Data Migration: Deductibles |  | In Review | NA | Thu Jun 05, 2025 | Mon Jun 23, 2025 | Tue Jul 29, 2025
FALSE | No | Rate Sheet Management |  |  | NA
FALSE | No | Set up / Manage Base Ratesheets |  | In Review | NA
FALSE | No | Clone Rate Sheets |  | Phase 2 | NA
FALSE | No | Data Migration: Ratesheets (Base and Coverages) | Naresh Pansuriya | In Progress | NA | Mon Aug 18, 2025
FALSE | No | Data Migration: Ratesheets (Surcharges, Deductibles) | Naresh Pansuriya | In Progress | NA | Mon Aug 18, 2025
FALSE | No | Accounts Payable |  |  | NA
TRUE | Yes | Accounts Receivable/Collections (Dealers) RPT202 - Dealer Receivable Report | Upendra | Not Started | NA
TRUE | Yes | Accounts Receivable - Aging (Dealers) RPT906 - Aging Dealer Balance Summary | Upendra | Not Started | NA
FALSE | No | Accounting |  |  | NA
TRUE | Yes | Vendor Data Reporting - Roadside |  | Not Started | NA
TRUE | Yes | Vendor Data Reporting - Old Republic |  | Not Started | NA
TRUE | Yes | Vendor Data Reporting - Diversicare |  | Not Started | NA
TRUE | Yes | Vendor Data Reporting - Vernon General |  | Not Started | NA
TRUE | Yes | Monthly Activity Reporting |  | Not Started | NA
TRUE | Yes | Underwriting |  |  | NA
TRUE | Yes | Earnings: R78/Pro/RR78/Proprietary |  | Not Started | NA
TRUE | Yes | Loss Ratio Reporting RPT632 - Loss Ratio Report |  | Not Started | NA
TRUE | Yes | Ultimate Loss Ratio |  | Not Started | NA
TRUE | Yes | Triangle Report Claims |  | Not Started | NA
TRUE | Yes | Triangle Report Cancellations |  | Not Started | NA
TRUE | Yes | Others |  |  | NA
TRUE | Yes | RPT160-List of Registers |  | Not Started | NA
TRUE | Yes | RPT161-Out of Balance Registers |  | Not Started | NA
TRUE | Yes | RPT164-List of Deposits |  | Not Started | NA
TRUE | Yes | RPT203-Cash Balancing Payments |  | Not Started | NA
TRUE | Yes | RPT600-Payee Statement |  | Not Started | NA
TRUE | Yes | RPT905-Dealer Billing Statement |  | Not Started | NA
TRUE | Yes | RPT1002-Invoice For Pending Contracts |  | Not Started | NA
TRUE | Yes | RPT569-Cancellation Details |  | Not Started | NA
TRUE | Yes | RPT565-Claim Paid Financial | Upendra | In Progress | NA | Mon Aug 18, 2025 | Thu Sep 04, 2025
TRUE | Yes | RPT631-Earnings Experience |  | Not Started | NA
|  | Notifications |  | In Review |  | Thu Aug 28, 2025 | Thu Sep 11, 2025
Last updated by |  | Gayatri Raol
Last udated date |  | 2025-09-16
Note on E1: Gayatri Raol: Status Not Started = Work has not been started Elicit Requirement = Requirement Gathering and Scoping In progress = Development in Progress Waiting= Waiting on Third party Hold = No activity due to dependencies or blocker Released = Feature ready and released Demo/Training = Scheduled Demo/Training In Review = Ascent is reviewing and providing feedback Done = Ascent Approved and closed Phase 2 = Future Release Rework = Redevelopment due to requirement change or predecessors
Note on C57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Require sandbox account - Chirag

## Roadmap for next two releases
Last updated by | Gayatri Raol
Last udated date | Sep, 03 2025
Release Date | Requirement Unclear | Tasks | Ongoing Tasks
2025-08-28 | FALSE | Claims & Reporting | Requirement Clarification – Valid Dealer Agent Rate Sheet Valid Coverage Check and ACH Integration Reinsurance Dealer Onboarding Critical Feedback QuickBooks (QB) NACHA PCRS Standard
| FALSE | Claims Feedback
| FALSE | Report 906
| FALSE | Report 565
| TRUE | Deductible
| FALSE | Authorization Number
2025-09-04 | FALSE | Dealer Onboarding Mapping | Requirements Clarification Reinsurance module Agent Rate sheet Client Feedback Report Generations Payment Tables Warehouse Tables
| FALSE | Dealer Wizard
| FALSE | Zoho Integration
| FALSE | Bulk Test Rate
| FALSE | Dealer Coverages
2025-09-15 | FALSE | Dealer Rate Sheets Implementation | Requirements Understanding Commissions Dealer Rate Sheets/Agent Rate Sheet- Sep 4 Migration Client Feedback Report Generations
FALSE
| FALSE | Contract Management
| FALSE | Contract Cancellation Workflow
| FALSE | Contract Cancellation Portal
| FALSE | Agent Dashboard
| TRUE | Agent Rate sheet
|  | Contract Cancellation | Shivani will schedule a meeting for Cancellation review - Sep 3
| FALSE | Cancellation Processing
| FALSE | Dealership ability to initiate Quotes or Cancellation & Notifiy Ascent
| FALSE | Initiate Process upon receipt of request = Cancellation workflow
| TRUE | Review for Dealer Status, NCB, Claims Paid, Cancel Fees | @Shivani will Schedule a call on Tuesday (Sep 9)
| FALSE | Lender Direct Cancellations (L5, Budco)
| TRUE | Diversicare Cancellations | Add to discuss this in Cancellation review meeting
| TRUE | Cancel Business to Cash Recon | Add to discussion list
| FALSE | Refund Type? Dealer Stmt Credit? Check or ACH
| TRUE | Prepare NACHA file for ACH Payments | Shivani need to review and get updates from Moksh
| TRUE | Prepare check file to import into QB | Ask Katrina & Karen for QB format template
Notificaiton
Send notification when a Claim Document is uploaded from the Servicer Dashboard
| FALSE | Notification when a Claim is added from the Portal
Oct 9-25 Reinsurance Module? | FALSE | Reinsurance
| FALSE | Configuration: Capture Deal
| FALSE | Claims Reserves
| FALSE | Earnings
| FALSE | Enter Expenses Paid/collected on Behalf
| FALSE | Rule Engine to setup Coverages, Rate Bucket, Seller and Allocation
| FALSE | Bank configuration and entering bank transactions
| FALSE | Listing of Transactions and ability to add Adjustments
| FALSE | Dashboard for respective Reinsurance
| TRUE | List of All Payments Due (Cession Funding)
| TRUE | List of all amounts to be collected (Reverse Cession Funding)
| TRUE | Journal Entries to Book
| TRUE | Cession Statements (Net) RPT901 - Cession Statement
| TRUE | Cession Statements (Retail)
| TRUE | Reconcile Biz to Reins Accounts
| TRUE | Reconcile Biz to Dealer Remittance
| TRUE | Reconcile Claims to Reins Accounts
| TRUE | Monthly Cash Analysis
| TRUE | Summary by Product
| TRUE | Contract Details
| TRUE | Claims Details
| TRUE | Reporting Packages (bolted together)
| TRUE | Trust /Custody/B Account Stmts (Bolt into Package)
| TRUE | Reporting Quarterly Cover
| TRUE | Report of Reinsurer Collateral
| TRUE | Report of Reinsurers by Domicile
Sep 25, 2025 Commission Module ? | TRUE | Commissions
| TRUE | Reconcile 908 to 600 Activation Basis
| TRUE | Prepare Statements
| TRUE | Prepare Commission Summary Reporting RTP681 Sales Commission Report
| TRUE | PM Carry Forward to Summary
| TRUE | Incorporate additions for advances/loans
| TRUE | Incorporate deductions for claims exceptions
| TRUE | Incorporate deductions for contract/surcharge payments
| TRUE | Incorporate deductions for advance/loan payback
| TRUE | Incorporate Payee Corrections/Calculations
| TRUE | Prepare NACHA file for ACH Payments
| TRUE | Prepare check file to import into QB
Email Statements to Payees

## Open Decision & Next Steps
Last updated by | Gayatri Raol
Last udated date | 2025-09-10
Type | Who | Agent Dashboard | Status | Comments
Decision | Matt/Madison | Decision pending on whether to differentiate claims paid by company funds vs. dealer funds. Requires input from finance/legal teams. | Open
Decision | Matt/Madison | Ongoing discussion about how much commission data sub-agents should see. Needs policy alignment. | Open
Decision | Matt/Madison | Thresholds for red/yellow/green indicators are not yet finalized. Requires agreement on what constitutes 'struggling' or 'at risk'. Red = 90 days of Not active & Non compliant, Yellow = 60 days of Not active & non compliant, Green = Active & Compliant. Black = Once 90 days are passed, then 30 days notice period before dealer becomes inactive | Complete
Task | Matt | Provide Demand Letter Template | Complete
Decision | Matt//Madison | Needs confirmation of what data each Agent vs Sub Agent role should access. May require user testing or feedback. | Open
Task | Matt | Matt to provide screen captures or drawings of preferred CRM views. Final layout depends on feedback. | Open
Decision | Madison | Madison mentioned openness to exploring new phone systems. Decision pending on replacement or integration. | Open
Contract Cancellation
Task | SDS | Create UI mockups for cancellation quote system | Complete | Probably Start development instead
Task | SDS | Explore faster payment options beyond ACH. Evaluate payment solutions for cancellations . As a team, we want to evaluate payment solutions for cancellations, so that we can offer efficient refund methods. | Open
Task | Ascent Team | Provide list of cancellation reasons. As a team, we want to discuss agent commissions, so that we can align on disbursement processes. | Complete
Meeting | SDS/Ascent Team | Discuss agent commissions
Task | Ascent | Review and finalize Kanban checklist and workflow | Complete
Onboarding
Task | Dattu/Shivani | Demo Zoho Integration or share recording | Open
Decision | Nikki/Madison | Update Dealer Profit Reduction section of Dealer Commission Page: Are the options dynamic or static | complete
Agent Commission
Task | Madison | Review and confirm the "Bucket Mappings" for the Master Agent Commision | Open

## List of CR_HotFixes_ENHCE
Last updated by | Gayatri Raol | Claim Related Feedback/Change Request/ Hot Fixes
Last udated date | 2025-09-16
Issue Type | Issue key | Summary | Priority | Parent summary | Status | Created
Bug |  | Gap Claim Payee details | Highest |  | DONE | 2025-09-16
Change Request | WAA-4204 | Claims > Payment Method: Make Date fields required | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-09-15 17:19
Enhancement | WAA-4191 | Claim Detail Page: Display "Date" below the "Status value" | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | READY FOR QA | 2025-09-15 09:22
Bug | WAA-4155 | GAP Claim Header: Missing Vehicle Location details | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-09-11 12:43
Change Request | WAA-4151 | Claims: "Date of Loss" should be a required field instead of "Ins. Settlement date." | DONE | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-09-11 12:40
Task | WAA-4123 | Remove Card Expire Validation | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-09-09 11:29
Task | WAA-4043 | Additional Benefits: Disable Lemon Squad API | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-03-09 12:14
Task | WAA-4010 | Dates in GAP claims changing | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-01-09 16:44
Change Request | WAA-3947 | Summary Tab: Denied and Informational line item calculations | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-08-28
Change Request | WAA-3903 | Servicer Dashboard: Send an email to claims team on new uploaded document | None | Clients Inputs / Suggestions / Bugs/Hot-Fixes | BACKLOG | 8/26/2025 12:55
Change Request | WAA-3889 | Across all modules - Update Tax Rates to 3 decimal points | Low | Clients Inputs / Suggestions / Bugs/Hot-Fixes | BACKLOG | 8/25/2025 12:31
Change Request | WAA-3886 | Update Tax Rates to 4 decimal points | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 8/25/2025 12:27
Enhancement | WAA-3810 | Display Deductible as Line Item in Email and Dashboard | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 8/18/2025 15:13
Task | WAA-3809 | Generate Authorization Number | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 8/18/2025 15:04
Change Request | WAA-3783 | Claim Summary → Grand Total table (Requested / Adjusted / Final columns) | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 8/13/2025 13:46
Task | WAA-3780 | Fix Deductible Calculation in Approved to Pay Emails | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 8/13/2025 13:35
Enhancement | WAA-3779 | Claims> Add an Alert for new uploaded document | Medium | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 8/13/2025 13:18
Change Request | WAA-3765 | Approved to pay email should go to the "payment email" and " service advisor email" | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-12-08 16:53
Enhancement | WAA-3754 | Failure Tab: Grand total by Claim | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-12-08 11:31
Task | WAA-3748 | Pull all deductibles from Contract | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-11-08 17:00
Change Request | WAA-3741 | Claim Portal: Insert Text | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-11-08 13:39
Change Request | WAA-3736 | Contracts Header: Add Agent info to identify removed or change Agents | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-11-08 13:12
Enhancement | WAA-3735 | Add Current Odometer to VIN popout | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-11-08 13:07
Task | WAA-3732 | GAP Claim Feedback changes | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-08-08 19:19
Task | WAA-3727 | Update FED TAX ID | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-08-08 13:34
Enhancement | WAA-3723 | Lemon Squad Inspection- Send an email to the RO when inspection is initiatied | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-08-08 13:17
Enhancement | WAA-3722 | Claim Header: Add Dealer Notes Indicator next to Dealer info | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-08-08 13:00
Change Request | WAA-3719 | Change Adjudication Status field Name to "Agent Notes" | Medium | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-08-08 12:54
Enhancement | WAA-3718 | Claim Kanban View: Add VIN or at least last 6 numbers in Kanban View | Medium | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-08-08 12:46
Enhancement | WAA-3717 | Claim Portal: Job Description> By Default add one line for labor and part minimum | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-08-08 12:36
Enhancement | WAA-3716 | Fix the Contract PDF document view resolution | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-08-08 12:17
Change Request | WAA-3709 | Update Dealer Profit Reduction section of Dealer Commission Page | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | ON HOLD | 2025-07-08 15:42
Story | WAA-3700 | Claim Status Summary- Log Report Daily | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-07-08 14:16
Task | WAA-3691 | Navigate to blank claim form to submit GAP claim | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-07-08 13:42
Change Request | WAA-3678 | Lender Page Changes - Dealer Wizard | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DEV IN PROGRESS | 2025-07-08 12:58
Change Request | WAA-3675 | Add Failure Part Section to the Lemon Squad API | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-07-08 10:04
Task | WAA-3671 | Setup an Email for new Claim submit | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-06-08 13:12
Task | WAA-3661 | Generate a daily log report of all the claims submitted thru portal | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | TO DO | 2025-05-08 17:43
Task | WAA-3658 | Service History: Calculation issue (Claims Paid to Date & Total Claims Incurred) | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-05-08 17:22
Enhancement | WAA-3656 | Claim Header: Make it Expanded | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-05-08 15:22
Enhancement | WAA-3655 | Show Latest Payee Address When Payment Method Is Switched to ‘Check’ | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-05-08 14:35
Task | WAA-3632 | City and State field: Claim portal page and Add Servicer internal page | Low | Clients Inputs / Suggestions / Bugs/Hot-Fixes | ON HOLD | 2025-03-08 22:57
Enhancement | WAA-3626 | Ability to Search Contracts by Customer | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-03-08 22:00
Change Request | WAA-3618 | Summary Tab: Add Status dropdown | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-01-08 15:33
Enhancement | WAA-3605 | Claim Header: Add Contract Status next/below the Contract number | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-01-08 13:33
Enhancement | WAA-3602 | Lemon Squad: Not Importing | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-01-08 13:28
Enhancement | WAA-3600 | Additional Benefits: Add Loss Code " Time and Mileage" | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-01-08 13:04
Enhancement | WAA-3599 | Payment method: Updates to add dates by payment method | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-01-08 12:56
Enhancement | WAA-3598 | Lemon Squad API: New API sending over claims | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-08-01 11:54
Change Request | WAA-3594 | Coverage: Apply Lemon Squad Inspection to all coverage | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/31/2025 16:48
Change Request | WAA-3588 | Payment Method: Add CVV code | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/31/2025 16:03
Change Request | WAA-3585 | Servicer Dashboard -Should not have access to private chats | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/31/2025 14:13
Change Request | WAA-3581 | Summary Tab : Deductible Waive off feature | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/31/2025 13:51
Change Request | WAA-3573 | Claims: workflow stage update | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/30/2025 18:30
Enhancement | WAA-3558 | Claims Page: Add VIN search option | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/30/2025 15:24
Change Request | WAA-3557 | Lemon Squad API - Change Pass type =7 | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/30/2025 15:18
Task | WAA-3553 | Servicer Dashboard & Email: Update Payment Method | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/30/2025 13:14
Change Request | WAA-3550 | LemonSquard Order Type "Standard" to "Mechanical" | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/30/2025 11:56
Enhancement | WAA-3547 | Claim Detail > Change the Bulk Approve part popup title | None | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/29/2025 18:56
Enhancement | WAA-3542 | Claims Header- Add Agent Info Column | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/29/2025 12:14
Change Request | WAA-3522 | Claim portals: Pull all contracts regardless of status | Low | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/28/2025 12:51
Task | WAA-3509 | Add disclaimer to the Authorized emails | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/25/2025 14:42
Task | WAA-3489 | Add CC to Authorization and Approved to Pay emails | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/23/2025 12:37
Enhancement | WAA-3488 | Develop notes template to standardize email response format- Future Release | Medium | Clients Inputs / Suggestions / Bugs/Hot-Fixes | BACKLOG | 7/23/2025 12:29
Enhancement | WAA-3485 | Claims Header - show list of contracts by VIN | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/23/2025 11:50
Change Request | WAA-3480 | Revamp Dealer Dashboard Notes Display + Add Claim Update Alerts | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/23/2025 11:23
Change Request | WAA-3477 | Transition Claim Status Logic to Chevron/Kanban Controls with New Status Set | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/23/2025 11:02
Change Request | WAA-3468 | claim portal updates: Multi Select Support" in Portal and displaying the value in Web | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/22/2025 14:33
Change Request | WAA-3445 | Summary Tab- Payee breakdown & Email preview and send action | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/21/2025 15:05
Change Request | WAA-3414 | Claim Authorization Email Notification: Update language & content | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/17/2025 14:25
Enhancement | WAA-3413 | Add payment type to the AP dashboard | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/17/2025 14:01
Change Request | WAA-3408 | Servicer Dashboard- Customization | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/17/2025 13:35
Enhancement | WAA-3384 | Add Reinsurance or Walkaway label to the claim page header | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/16/2025 12:55
Change Request | WAA-3379 | Update Virtual Card Tab to "Payment Method" with Dynamic Field Logic | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/16/2025 12:40
Task | WAA-3378 | Updates to Mechanical claim portal form | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/16/2025 12:28
Story | WAA-3352 | Allow Adjudicator ability to bulk edit options | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 7/14/2025 18:31
Task | WAA-3331 | Update/ Change Contract number on Claim edit page | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-10-07 18:42
Task | WAA-3330 | Ability to select from multiple contracts when claim submitted thru all 3 portals (Mechanical, Tesla, Appearance) | Medium | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-10-07 18:17
Task | WAA-3328 | Contract Number validation | Medium | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-10-07 17:00
Task | WAA-3309 | Claims Failure Part Popup: Set user focus on after 0 value for Currency and mask control | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-09-07 15:23
Task | WAA-3292 | Adjudicator Cannot Edit Loss Code Assigned to Failure Parts | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-08-07 23:37
Task | WAA-3279 | Post Claims Review Status Prevents Any Claim Actions | High | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-08-07 11:51
Task | WAA-3278 | Approved Claims Still Visible on Adjuster Dashboard | Medium | Clients Inputs / Suggestions / Bugs/Hot-Fixes | IN PO/TL REVIEW | 2025-08-07 11:49
Change Request | WAA-3275 | "What Type of Claim?" Field Inappropriately Required for Mechanical Claims | Medium | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-08-07 11:48
Enhancement | WAA-3274 | Claims Manager Cannot View All Active Contracts Associated with VIN | Medium | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-08-07 11:44
Task | WAA-3273 | Claims AP Role View Showing Incorrect Claim Stages | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-08-07 11:43
Task | WAA-3272 | Claims Manager Role Missing Access to Full Claim Lifecycle Stages | Highest | Clients Inputs / Suggestions / Bugs/Hot-Fixes | DONE | 2025-08-07 11:41

## Data Migration Updates
Last Updated | 2025-09-15 | By: | Naresh | 2025-09-15 |  |  | 2025-09-14 |  |  | 2025-09-13 |  |  | 2025-09-12 |  |  | 2025-09-11 |  |  | 2025-09-10 |  |  | 2025-09-09 |  |  | 2025-09-08 |  |  | 2025-09-07 |  |  | 2025-09-06 |  |  | 2025-09-05 |  |  | 2025-09-04 |  |  | 2025-09-03 |  |  | 2025-09-02 |  |  | 2025-09-01 |  |  | 2025-08-31 |  |  | 2025-08-30 |  |  | 8/29/2025 |  |  | 8/28/2025 |  |  | 8/27/2025 |  |  | 8/26/2025 |  |  | 8/25/2025 |  |  | 8/22/2025 |  |  | 8/21/2025 |  |  | 8/20/2025 |  |  | 8/19/2025 |  |  | 8/18/2025 |  |  | 8/15/2025 |  |  | 8/14/2025 |  |  | 8/13/2025 |  |  | 2025-12-08 |  |  | 2025-11-08 |  |  | 2025-08-08 |  |  | 2025-07-08 |  |  | 2025-06-08 |  |  | 2025-05-08 |  |  | 2025-04-08 |  |  | 2025-01-08 |  |  | 7/31/2025 |  |  | 7/30/2025 |  |  | 7/29/2025 |  |  | 7/26/2025 |  |  | 7/25/2025 |  |  | 7/24/2025 |  |  | 7/23/2025 |  |  | 7/22/2025 |  |  | 7/21/2025 |  |  | 7/18/2025 |  |  | 7/17/2025 |  |  | 7/16/2025 |  |  | 7/15/2025 |  |  | 7/14/2025 |  |  | 2025-11-07 |  |  | 2025-09-07 |  |  | 2025-08-07 |  |  | 2025-07-07 |  |  | 2025-04-07 |  |  | 2025-03-07 |  |  | 2025-02-07 |  |  | 2025-01-07 |  |  | 6/30/2025 |  |  | 6/27/2025 |  |  | 6/26/2025 |  |  | 6/25/2025 |  |  | 6/24/2025
# | Module | Sub-Module | Source | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD % | Total Records | PROD | PROD %
1 | Claims |  | Auto | 5725 | 5725 | 100 | 5725 | 5725 | 100 | 5725 | 5725 | 100 | 5725 | 5725 | 100 | 5725 | 5725 | 100 | 5725 | 5725 | 100 | 5718 | 5718 | 100 | 5718 | 5718 | 100 | 5718 | 5718 | 100 | 5718 | 5718 | 100 | 5718 | 5718 | 100 | 5718 | 5718 | 100 | 5718 | 5718 | 100 | 5718 | 5718 | 100 | 5718 | 5718 | 100 | 5718 | 5718 | 100 | 5718 | 5718 | 100 | 5718 | 5718 | 100 | 5707 | 5707 | 100 | 5707 | 5707 | 100 | 5707 | 5707 | 100 | 5707 | 5707 | 100 | 5707 | 5707 | 100 | 5707 | 5707 | 100 | 5707 | 5707 | 100 | 5707 | 5707 | 100 | 5707 | 5707 | 100 | 5707 | 5707 | 100 | 5707 | 5705 | 99.96 | 5705 | 5705 | 100 |  |  |  | 5705 | 5705 | 100 | 5704 | 5704 | 100 | 5689 | 5689 | 100 | 5689 | 5689 | 100 | 5689 | 5689 | 100 | 5687 | 5687 | 100 | 5686 | 5686 | 100 | 5684 | 5684 | 100 | 5681 | 5680 | 99.98 | 5680 | 5680 | 100 | 5659 | 5659 | 100 | 5604 | 5604 | 100 | 5604 | 5604 | 100 | 5604 | 5604 | 100 | 5576 | 5576 | 100 | 5557 | 5557 | 100 | 5531 | 5531 | 100 | 5507 | 5507 | 100 | 5465 | 5465 | 100 | 5465 | 5465 | 100 | 5444 | 5444 | 100 | 5422 | 5400 | 99.59 | 5377 | 5377 | 100 | 5356 | 5356 | 100 | 5332 | 5332 | 100 | 5323 | 5323 | 100 | 5310 | 5310 | 100 | 5273 | 5273 | 100 | 5244 | 5244 | 100 | 5220 | 5220 | 100 | 5175 | 5175 | 100 | 5175 | 5175 | 100 | 5152 | 5152 | 100% | 5124 | 5124 | 100%
2 | Servicers |  | Auto | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 | 2125 | 2125 | 100 |  |  |  | 2125 | 2125 | 100 | 2125 | 2117 | 99.62 | 2125 | 2117 | 99.62 | 2125 | 2117 | 99.62 | 2125 | 2117 | 99.62 | 2125 | 2117 | 99.62 | 2125 | 2117 | 99.62 | 2125 | 2117 | 99.62 | 2125 | 2117 | 99.62 | 2125 | 2117 | 99.62 | 2120 | 2112 | 99.62 | 2098 | 2099 | 100.1 | 2098 | 2099 | 100.1 | 2098 | 2090 | 99.62 | 2091 | 2083 | 99.62 | 2083 | 2075 | 99.62 | 2078 | 2070 | 99.62 | 2068 | 2060 | 99.61 | 2053 | 2060 | 100.34 | 2053 | 2053 | 100 | 2042 | 2042 | 100 | 2030 | 2030 | 100 | 2009 | 2001 | 99.6 | 2001 | 2001 | 100 | 1992 | 1992 | 100 | 1992 | 1992 | 100 | 1990 | 1981 | 99.55 | 1981 | 1981 | 100 | 1977 | 1977 | 100 | 1970 | 1970 | 100 | 1950 | 1944 | 99.69 | 1950 | 1944 | 99.69 | 1944 | 1944 | 100% | 1937 | 1930 | 99.64%
3 | Contracts |  | Auto | 160840 | 160840 | 100 | 160303 | 160303 | 100 | 160303 | 160303 | 100 | 159697 | 159697 | 100 | 159697 | 159697 | 100 | 159491 | 159491 | 100 | 159228 | 159228 | 100 | 158972 | 158972 | 100 | 158914 | 158914 | 100 | 156823 | 156823 | 100 | 156599 | 156599 | 100 | 156599 | 156599 | 100 | 156323 | 156323 | 100 | 155988 | 155988 | 100 | 155711 | 155711 | 100 | 155608 | 155608 | 100 | 155155 | 155155 | 100 | 154728 | 154728 | 100 | 154404 | 154404 | 100 | 153903 | 153903 | 100 | 153656 | 153656 | 100 | 153373 | 153373 | 100 | 152479 | 152479 | 100 | 152211 | 152211 | 100 | 151839 | 151839 | 100 | 151462 | 151462 | 100 | 149335 | 149335 | 100 | 148437 | 148437 | 100 | 148184 | 148184 | 100 | 147704 | 147704 | 100 |  |  |  | 147462 | 147462 | 100 | 146634 | 146634 | 100 | 146396 | 146396 | 100 | 146107 | 146107 | 100 | 145875 | 145875 | 100 | 145611 | 145611 | 100 | 144900 | 144900 | 100 | 144570 | 144570 | 100 | 144190 | 143961 | 99.84 | 143961 | 143961 | 100 | 143210 | 143210 | 100 | 141821 | 141821 | 100 | 141821 | 141821 | 100 | 141821 | 141821 | 100 | 141448 | 141448 | 100 | 141175 | 141175 | 100 | 140027 | 140027 | 100 | 139759 | 139759 | 100 | 139318 | 139318 | 100 | 139318 | 139318 | 100 | 139078 | 139078 | 100 | 138414 | 138152 | 99.81 | 137924 | 137924 | 100 | 137703 | 137703 | 100 | 137423 | 137423 | 100 | 137022 | 137022 | 100 | 136748 | 136748 | 100 | 135053 | 135053 | 100 | 134858 | 134858 | 100 | 134585 | 134585 | 100 | 133731 | 133731 | 100 | 133731 | 133731 | 100 | 133530 | 133530 | 100% | 133296 | 133296 | 100%
4 | Agents |  | Auto | 410 | 410 | 100 | 410 | 410 | 100 | 410 | 410 | 100 | 410 | 410 | 100 | 410 | 410 | 100 | 410 | 410 | 100 | 410 | 410 | 100 | 408 | 408 | 100 | 408 | 408 | 100 | 406 | 406 | 100 | 406 | 406 | 100 | 406 | 406 | 100 | 406 | 406 | 100 | 406 | 406 | 100 | 406 | 406 | 100 | 406 | 406 | 100 | 406 | 406 | 100 | 406 | 406 | 100 | 404 | 404 | 100 | 404 | 404 | 100 | 400 | 400 | 100 | 397 | 397 | 100 | 397 | 397 | 100 | 397 | 397 | 100 | 397 | 397 | 100 | 396 | 396 | 100 | 396 | 396 | 100 | 396 | 396 | 100 | 396 | 396 | 100 | 395 | 395 | 100 |  |  |  | 395 | 395 | 100 | 395 | 395 | 100 | 394 | 394 | 100 | 394 | 394 | 100 | 394 | 394 | 100 | 394 | 394 | 100 | 393 | 393 | 100 | 392 | 392 | 100 | 392 | 391 | 99.74 | 392 | 392 | 100 | 387 | 387 | 100 | 387 | 387 | 100 | 387 | 387 | 100 | 387 | 387 | 100 | 386 | 386 | 100 | 386 | 386 | 100 | 386 | 386 | 100 | 383 | 383 | 100 | 382 | 382 | 100 | 382 | 382 | 100 | 381 | 381 | 100 | 381 | 381 | 100 | 378 | 378 | 100 | 378 | 378 | 100 | 378 | 378 | 100 | 378 | 378 | 100 | 377 | 377 | 100 | 376 | 376 | 100 | 374 | 374 | 100 | 374 | 374 | 100 | 373 | 373 | 100 | 373 | 373 | 100 | 373 | 373 | 100% | 373 | 373 | 100%
5 | Dealers | Details | Auto | 2190 | 2190 | 100 | 2189 | 2189 | 100 | 2189 | 2189 | 100 | 2186 | 2186 | 100 | 2186 | 2186 | 100 | 2184 | 2184 | 100 | 2183 | 2183 | 100 | 2176 | 2176 | 100 | 2176 | 2176 | 100 | 2172 | 2172 | 100 | 2170 | 2170 | 100 | 2170 | 2170 | 100 | 2166 | 2166 | 100 | 2166 | 2166 | 100 | 2166 | 2166 | 100 | 2166 | 2166 | 100 | 2166 | 2166 | 100 | 2162 | 2162 | 100 | 2156 | 2156 | 100 | 2152 | 2152 | 100 | 2149 | 2149 | 100 | 2144 | 2144 | 100 | 2140 | 2140 | 100 | 2139 | 2139 | 100 | 2135 | 2135 | 100 | 2133 | 2133 | 100 | 2131 | 2131 | 100 | 2130 | 2130 | 100 | 2128 | 2128 | 100 | 2124 | 2124 | 100 |  |  |  | 2123 | 2123 | 100 | 2123 | 2123 | 100 | 2122 | 2122 | 100 | 2119 | 2119 | 100 | 2118 | 2118 | 100 | 2118 | 2118 | 100 | 2115 | 2115 | 100 | 2109 | 2109 | 100 | 2105 | 2105 | 100 | 2104 | 2104 | 100 | 2095 | 2095 | 100 | 2085 | 2085 | 100 | 2085 | 2085 | 100 | 2085 | 2085 | 100 | 2085 | 2085 | 100 | 2083 | 2083 | 100 | 2079 | 2079 | 100 | 2076 | 2076 | 100 | 2071 | 2071 | 100 | 2071 | 2071 | 100 | 2069 | 2069 | 100 | 2068 | 2068 | 100 | 2063 | 2063 | 100 | 2063 | 2063 | 100 | 2059 | 2059 | 100 | 2059 | 2059 | 100 | 2056 | 2056 | 100 | 2051 | 2051 | 100 | 2050 | 2050 | 100 | 2046 | 2046 | 100 | 2041 | 2041 | 100 | 2041 | 2041 | 100 | 2039 | 2039 | 100% | 2035 | 2035 | 100%
|  | Rates | Manual
|  | Markup | Manual
6 | Insurance Companies | Details | Auto | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 |  |  |  | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100 | 7 | 7 | 100% | 7 | 7 | 100%
7 | Participation Companies |  | Manual | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 |  |  |  | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100 | 63 | 63 | 100% | 63 | 63 | 100%
8 | Earning Curves |  | Auto | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 |  |  |  | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100 | 70 | 70 | 100% | 70 | 70 | 100%
9 | Earning Groups |  | Auto | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 |  |  |  | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100% | 5 | 5 | 100%
10 | Earning Assignments |  | Auto | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 |  |  |  | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100 | 2 | 2 | 100% | 2 | 2 | 100%
11 | Earning Sets |  | Auto | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 |  |  |  | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100 | 3 | 3 | 100% | 3 | 3 | 100%
12 | Incentive Programs |  | Manual | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 |  |  |  | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100 | 162 | 162 | 100% | 162 | 162 | 100%
13 | Lenders |  | Auto | 2709 | 2709 | 100 | 2707 | 2707 | 100 | 2707 | 2707 | 100 | 2695 | 2695 | 100 | 2695 | 2695 | 100 | 2694 | 2694 | 100 | 2692 | 2692 | 100 | 2684 | 2684 | 100 | 2684 | 2684 | 100 | 2678 | 2678 | 100 | 2674 | 2674 | 100 | 2674 | 2674 | 100 | 2668 | 2668 | 100 | 2667 | 2667 | 100 | 2664 | 2664 | 100 | 2662 | 2662 | 100 | 2660 | 2660 | 100 | 2659 | 2659 | 100 | 2655 | 2655 | 100 | 2652 | 2652 | 100 | 2649 | 2649 | 100 | 2644 | 2644 | 100 | 2634 | 2634 | 100 | 2633 | 2633 | 100 | 2631 | 2631 | 100 | 2628 | 2628 | 100 | 2626 | 2626 | 100 | 2618 | 2618 | 100 | 2614 | 2614 | 100 | 2609 | 2609 | 100 |  |  |  | 2607 | 2600 | 99.73 | 2602 | 2587 | 99.42 | 2601 | 2587 | 99.46 | 2596 | 2587 | 99.65 | 2590 | 2587 | 99.88 | 2588 | 2585 | 99.88 | 2580 | 2577 | 99.88 | 2573 | 2570 | 99.88 | 2569 | 2561 | 99.69 | 2564 | 2561 | 99.88 | 2558 | 2555 | 99.88 | 2545 | 2550 | 100.2 | 2545 | 2550 | 100.2 | 2545 | 2542 | 99.88 | 2536 | 2533 | 99.88 | 2532 | 2529 | 99.88 | 2518 | 2515 | 99.88 | 2516 | 2513 | 99.88 | 2509 | 2513 | 100.16 | 2509 | 2509 | 100 | 2506 | 2506 | 100 | 2501 | 2501 | 100 | 2495 | 2493 | 99.92 | 2493 | 2493 | 100 | 2484 | 2484 | 100 | 2483 | 2483 | 100 | 2481 | 2472 | 99.64 | 2472 | 2472 | 100 | 2466 | 2466 | 100 | 2464 | 2464 | 100 | 2451 | 2445 | 99.76 | 2451 | 2445 | 99.76 | 2445 | 2445 | 100% | 2442 | 2442 | 100%
14 | Coverages |  | Auto | 323 | 378 | 117.03 | 323 | 378 | 117.03 | 323 | 378 | 117.03 | 319 | 374 | 117.24 | 319 | 374 | 117.24 | 317 | 372 | 117.35 | 313 | 368 | 117.57 | 313 | 368 | 117.57 | 312 | 367 | 117.63 | 312 | 367 | 117.63 | 312 | 367 | 117.63 | 312 | 367 | 117.63 | 312 | 367 | 117.63 | 312 | 367 | 117.63 | 312 | 367 | 117.63 | 312 | 367 | 117.63 | 312 | 367 | 117.63 | 312 | 367 | 117.63 | 312 | 367 | 117.63 | 311 | 366 | 117.68 | 311 | 366 | 117.68 | 311 | 366 | 117.68 | 309 | 364 | 117.8 | 309 | 364 | 117.8 | 309 | 364 | 117.8 | 309 | 364 | 117.8 | 309 | 364 | 117.8 | 308 | 363 | 117.86 | 309 | 363 | 117.48 | 305 | 359 | 117.7 |  |  |  | 304 | 358 | 117.76 | 304 | 358 | 117.76 | 304 | 358 | 117.76 | 304 | 358 | 117.76 | 304 | 358 | 117.76 | 304 | 358 | 117.76 | 304 | 358 | 117.76 | 302 | 356 | 117.88 | 302 | 356 | 117.88 | 302 | 356 | 117.88 | 302 | 356 | 117.9 | 302 | 356 | 117.9 | 302 | 356 | 117.9 | 302 | 356 | 117.9 | 302 | 356 | 117.9 | 302 | 356 | 117.9 | 300 | 354 | 118 | 300 | 354 | 118 | 300 | 354 | 118 | 300 | 354 | 118 | 295 | 349 | 118.31 | 291 | 345 | 118.6 | 290 | 355 | 122.4 | 287 | 403 | 140.4 | 287 | 403 | 140.4 | 287 | 403 | 140.42 | 286 | 402 | 140.6 | 286 | 402 | 140.56 | 289 | 402 | 139.1 | 286 | 399 | 139.51 | 282 | 395 | 140.07 | 282 | 395 | 140.07 | 282 | 395 | 140.1% | 282 | 395 | 140.1%
15 | Coverage Groups |  | Auto | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 |  |  |  | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 168 | 800 | 21 | 453 | 2157 | 21 | 453 | 2157 | 21 | 453 | 2157 | 21 | 293 | 1395.2 | 21 | 281 | 1338 | 21 | 160 | 761.9 | 21 | 160 | 761.9 | 21 | 160 | 761.9 | 21 | 160 | 761.9 | 21 | 160 | 761.9 | 21 | 160 | 761.9% | 21 | 160 | 761.9%
16 | Cancellation Methods |  | Auto | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 |  |  |  | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100 | 5 | 5 | 100% | 5 | 5 | 100%
17 | Cancellation Rules |  | Manual | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 |  |  |  | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100 | 27 | 27 | 100% | 27 | 27 | 100%
18 | Brands |  | N/A | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 |  |  |  | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 18 | 120 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100% | 15 | 15 | 100%
19 | Product Types |  | Auto | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 |  |  |  | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100 | 15 | 15 | 100% | 15 | 15 | 100%
20 | Components/Surcharges |  | Auto | 1877 | 1878 | 100.05 | 1877 | 1878 | 100.05 | 1877 | 1878 | 100.05 | 1873 | 1874 | 100.05 | 1873 | 1874 | 100.05 | 1873 | 1874 | 100.05 | 1873 | 1874 | 100.05 | 1873 | 1874 | 100.05 | 1871 | 1872 | 100.05 | 1871 | 1872 | 100.05 | 1871 | 1872 | 100.05 | 1871 | 1872 | 100.05 | 1871 | 1872 | 100.05 | 1871 | 1872 | 100.05 | 1871 | 1872 | 100.05 | 1871 | 1872 | 100.05 | 1871 | 1872 | 100.05 | 1871 | 1872 | 100.05 | 1871 | 1872 | 100.05 | 1871 | 1872 | 100.05 | 1871 | 1872 | 100.05 | 1871 | 1872 | 100.05 | 1870 | 1871 | 100.05 | 1870 | 1871 | 100.05 | 1870 | 1871 | 100.05 | 1870 | 1871 | 100.05 | 1870 | 1871 | 100.05 | 1870 | 1871 | 100.05 | 1867 | 1867 | 100 | 1867 | 1867 | 100 |  |  |  | 1867 | 1867 | 100 | 1867 | 1867 | 100 | 1867 | 1867 | 100 | 1867 | 1867 | 100 | 1867 | 1867 | 100 | 1867 | 1867 | 100 | 1867 | 1867 | 100 | 1867 | 1867 | 100 | 1867 | 1867 | 100 | 1867 | 1867 | 100 | 1867 | 1867 | 100 | 1867 | 1867 | 100 | 1867 | 1867 | 100 | 1867 | 1867 | 100 | 1866 | 1866 | 100 | 1866 | 1866 | 100 | 1866 | 1866 | 100 | 1866 | 1866 | 100 | 1866 | 1866 | 100 | 1866 | 1866 | 100 | 1866 | 1866 | 100 | 1866 | 1866 | 100 | 1865 | 1865 | 100 | 1865 | 1865 | 100 | 1865 | 1865 | 100 | 1865 | 1865 | 100 | 1865 | 1865 | 100 | 1865 | 1865 | 100 | 1865 | 1865 | 100 | 1865 | 1865 | 100 | 1853 | 1853 | 100 | 1853 | 1853 | 100 | 1853 | 1853 | 100% | 1853 | 1853 | 100%
21 | Eligibility Tiers |  | Manual | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 |  |  |  | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 39 | 100 | 39 | 34 | 87.18 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100 | 34 | 34 | 100% | 34 | 34 | 100%
22 | Form Profiles |  | Auto | 240 | 244 | 101.67 | 240 | 244 | 101.67 | 240 | 244 | 101.67 | 239 | 240 | 100.42 | 236 | 240 | 101.69 | 234 | 238 | 101.71 | 234 | 238 | 101.71 | 234 | 238 | 101.71 | 233 | 237 | 101.72 | 233 | 237 | 101.72 | 233 | 237 | 101.72 | 233 | 237 | 101.72 | 233 | 237 | 101.72 | 233 | 237 | 101.72 | 233 | 237 | 101.72 | 233 | 237 | 101.72 | 233 | 237 | 101.72 | 233 | 237 | 101.72 | 233 | 237 | 101.72 | 232 | 236 | 101.72 | 232 | 236 | 101.72 | 232 | 236 | 101.72 | 232 | 236 | 101.72 | 232 | 236 | 101.72 | 232 | 236 | 101.72 | 231 | 235 | 101.73 | 231 | 235 | 101.73 | 230 | 234 | 101.74 | 230 | 233 | 101.3 | 229 | 232 | 101.31 |  |  |  | 228 | 232 | 101.75 | 230 | 230 | 100 | 230 | 230 | 100 | 230 | 230 | 100 | 230 | 230 | 100 | 230 | 230 | 100 | 230 | 230 | 100 | 230 | 230 | 100 | 230 | 230 | 100 | 230 | 230 | 100 | 230 | 230 | 100 | 230 | 226 | 98.26 | 226 | 226 | 100 | 226 | 226 | 100 | 223 | 223 | 100 | 222 | 222 | 100 | 220 | 220 | 100 | 220 | 220 | 100 | 220 | 220 | 100 | 220 | 220 | 100 | 219 | 219 | 100 | 217 | 214 | 98.62 | 211 | 211 | 100 | 211 | 211 | 100 | 211 | 211 | 100 | 211 | 211 | 100 | 208 | 208 | 100 | 208 | 208 | 100 | 208 | 208 | 100 | 208 | 208 | 100 | 208 | 207 | 99.52 | 207 | 207 | 100 | 49 | 50 | 100% | 49 | 50 | 100%
23 | Forms |  | Auto | 58 | 58 | 100 | 58 | 58 | 100 | 58 | 58 | 100 | 57 | 57 | 100 | 57 | 57 | 100 | 55 | 55 | 100 | 55 | 55 | 100 | 55 | 55 | 100 | 55 | 55 | 100 | 55 | 55 | 100 | 55 | 55 | 100 | 55 | 55 | 100 | 55 | 55 | 100 | 55 | 55 | 100 | 55 | 55 | 100 | 55 | 55 | 100 | 55 | 55 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 |  |  |  | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 53 | 98.15 | 53 | 53 | 100 | 53 | 53 | 100 | 51 | 51 | 100 | 51 | 51 | 100 | 51 | 51 | 100 | 51 | 51 | 100 | 51 | 51 | 100 | 51 | 51 | 100 | 51 | 51 | 100 | 51 | 51 | 100 | 51 | 51 | 100 | 51 | 51 | 100 | 51 | 51 | 100 | 51 | 51 | 100 | 50 | 50 | 100 | 50 | 50 | 100 | 50 | 50 | 100 | 50 | 50 | 100 | 50 | 50 | 100 | 50 | 50 | 100 | 207 | 207 | 100% | 207 | 207 | 100%
24 | Vehicle Classification |  | Manual | 66 | 66 | 100 | 66 | 66 | 100 | 66 | 66 | 100 | 64 | 64 | 100 | 64 | 64 | 100 | 64 | 64 | 100 | 62 | 62 | 100 | 62 | 62 | 100 | 62 | 62 | 100 | 62 | 62 | 100 | 62 | 62 | 100 | 62 | 62 | 100 | 62 | 62 | 100 | 62 | 62 | 100 | 62 | 62 | 100 | 62 | 62 | 100 | 62 | 62 | 100 | 62 | 62 | 100 | 62 | 62 | 100 | 61 | 61 | 100 | 61 | 61 | 100 | 61 | 61 | 100 | 60 | 60 | 100 | 60 | 60 | 100 | 60 | 60 | 100 | 60 | 60 | 100 | 60 | 60 | 100 | 60 | 60 | 100 | 59 | 59 | 100 | 57 | 57 | 100 |  |  |  | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 56 | 56 | 100 | 55 | 55 | 100 | 55 | 55 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 54 | 54 | 100 | 52 | 52 | 100 | 52 | 52 | 100 | 50 | 50 | 100% | 50 | 52 | 82.65%
25 | Payees |  | Auto | 644 | 644 | 100 | 642 | 642 | 100 | 642 | 642 | 100 | 642 | 642 | 100 | 642 | 642 | 100 | 642 | 642 | 100 | 641 | 641 | 100 | 637 | 637 | 100 | 637 | 637 | 100 | 637 | 637 | 100 | 633 | 633 | 100 | 633 | 633 | 100 | 633 | 633 | 100 | 633 | 633 | 100 | 632 | 632 | 100 | 632 | 632 | 100 | 631 | 631 | 100 | 630 | 630 | 100 | 629 | 629 | 100 | 629 | 629 | 100 | 628 | 628 | 100 | 626 | 626 | 100 | 626 | 626 | 100 | 625 | 625 | 100 | 625 | 625 | 100 | 623 | 623 | 100 | 622 | 622 | 100 | 622 | 622 | 100 | 622 | 622 | 100 | 622 | 622 | 100 |  |  |  | 621 | 621 | 100 | 621 | 621 | 100 | 620 | 620 | 100 | 619 | 619 | 100 | 619 | 619 | 100 | 619 | 619 | 100 | 617 | 617 | 100 | 613 | 613 | 100 | 612 | 612 | 100 | 612 | 612 | 100 | 607 | 607 | 100 | 603 | 603 | 100 | 603 | 603 | 100 | 603 | 603 | 100 | 603 | 603 | 100 | 603 | 603 | 100 | 603 | 603 | 100 | 601 | 601 | 100 | 599 | 599 | 100 | 599 | 599 | 100 | 599 | 599 | 100 | 598 | 598 | 100 | 595 | 595 | 100 | 595 | 595 | 100 | 594 | 594 | 100 | 594 | 594 | 100 | 594 | 594 | 100 | 594 | 594 | 100 | 594 | 594 | 100 | 593 | 593 | 100 | 591 | 591 | 100 | 591 | 591 | 100 | 590 | 590 | 100% | 587 | 587 | 82.65%

## Important Links
Last Updated | 7/29/2025 | BY: | Shivani
Name | Purpose | BOS BETA | BOS PROD | Notes
Web | Manage Coverages, Contracts, Claims and view Reports | https://beta.app.waas.sdsaz.us/ | https://app.waas.sdsaz.us/
Mechanical Claims | Add Mechanical Claim, by Repair Shop | https://beta.portal.do.sdsaz.us/MECHANICAL_CLAIM_WIZARD | https://portal.waas.sdsaz.us/fileaclaim
Appearance Claims | Add Appearance Claim, by Repair Shop or End User | https://beta.portal.do.sdsaz.us/APPEARANCE_CLAIM_WIZARD | https://portal.waas.sdsaz.us/appearanceclaim
Tesla Claims | Add Tesla Claim, by Repair Shop or End User | https://beta.portal.do.sdsaz.us/TESLA_CLAIM_WIZARD | https://portal.waas.sdsaz.us/teslaclaim
Dealer Onboarding | Onboard new Dealer | https://beta.portal.do.sdsaz.us/dealer_wizard | https://portal.waas.sdsaz.us/dealer_wizard